## Diagrama previsión
VEHICLEGEST
ILERNA ONLINE | Comienzo del proyecto: | 2022-10-20
Carlos Caruncho | Hoy: | 2022-12-05
| Visualizar semana | 1 |  |  | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05
 | time axis 2022-10-17 to 2022-12-11
TAREA | PROGRESO | COMIENZO | FIN | DÍAS | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d
Iniciación |  | 2022-10-17 | 2022-10-18 | 2
Elección de la temática | 100% | 2022-10-17 | 2022-10-18 | 2
Estudio de mercado | 100% | 2022-10-17 | 2022-10-18 | 2
Elección de tecnologías | 100% | 2022-10-17 | 2022-10-18 | 2
Definición ciclo de vida del proyecto | 100% | 2022-10-17 | 2022-10-18 | 2
Creación del repositorio | 100% | 2022-10-17 | 2022-10-18 | 2
Planificación |  | 2022-10-19 | 2022-10-25 | 7
Creación del repositorio | 100% | 2022-10-19 | 2022-10-20 | 2
Selección de la metodología | 100% | 2022-10-20 | 2022-10-21 | 2
Diagrama de Gantt | 100% | 2022-10-22 | 2022-10-24 | 3
Tablero Kanban | 100% | 2022-10-24 | 2022-10-25 | 2
Ejecución-Análisis |  | 2022-10-26 | 2022-10-31 | 6
Definición de requisitos | 100% | 2022-10-26 | 2022-10-27 | 2
Diagrama Entidad-Relación | 100% | 2022-10-27 | 2022-10-28 | 2
Diagrama Relacional | 100% | 2022-10-28 | 2022-10-29 | 2
Diagrama de clases | 100% | 2022-10-29 | 2022-10-30 | 2
Diagrama de casos de uso | 100% | 2022-10-30 | 2022-10-31 | 2
Ejecución-Diseño |  | 2022-11-01 | 2022-11-01 | 1
Boceto | 100% | 2022-11-01 | 2022-11-01 | 1
Ejecución-Codificación |  | 2022-11-02 | 2022-11-28 | 27
Autenticación | 100% | 2022-11-02 | 2022-11-02 | 1
Implementar menús | 100% | 2022-11-03 | 2022-11-04 | 2
Listado de vehículos | 100% | 2022-11-05 | 2022-11-06 | 2
Detalle de vehículo | 100% | 2022-11-07 | 2022-11-07 | 1
Creación de vehículo | 100% | 2022-11-08 | 2022-11-08 | 1
Edición de vehículos | 100% | 2022-11-09 | 2022-11-09 | 1
Eliminación de vehículo | 100% | 2022-11-10 | 2022-11-10 | 1
Listado de items de inventario | 100% | 2022-11-11 | 2022-11-11 | 1
Detalle de items de inventario | 100% | 2022-11-12 | 2022-11-12 | 1
Creación de items de inventario | 100% | 2022-11-13 | 2022-11-13 | 1
Edición de item de inventario | 100% | 2022-11-14 | 2022-11-14 | 1
Eliminación de item de inventario | 100% | 2022-11-15 | 2022-11-15 | 1
Listado de deficiencias | 100% | 2022-11-16 | 2022-11-16 | 1
Creación de deficiencias | 100% | 2022-11-17 | 2022-11-17 | 1
Detalle de deficiencias | 100% | 2022-11-18 | 2022-11-18 | 1
Edición de deficiencias | 100% | 2022-11-19 | 2022-11-19 | 1
Eliminación de deficiencias | 100% | 2022-11-20 | 2022-11-20 | 1
Listado de usuarios | 100% | 2022-11-21 | 2022-11-21 | 1
Detalle de usuarios | 100% | 2022-11-22 | 2022-11-22 | 1
Creación de usuarios | 100% | 2022-11-23 | 2022-11-23 | 1
Edición de usuarios | 100% | 2022-11-24 | 2022-11-24 | 1
Eliminación de usuarios | 100% | 2022-11-25 | 2022-11-25 | 1
Listado de ITVs | 100% | 2022-11-26 | 2022-11-26 | 1
Listado de alertas | 100% | 2022-11-27 | 2022-11-27 | 1
Generación de alertas | 100% | 2022-11-28 | 2022-11-28 | 1
Eliminación de alertas | 100% | 2022-11-29 | 2022-11-29 | 1
Ejecución-Pruebas |  | 2022-11-30 | 2022-11-30 | 1
Prueba de autenticación | 100% | 2022-12-01 | 2022-12-01 | 1
Pruebas de creación | 100% | 2022-12-02 | 2022-12-02 | 1
Pruebas de edición | 100% | 2022-12-03 | 2022-12-03 | 1
Pruebas de eliminación | 100% | 2022-12-04 | 2022-12-04 | 1
Pruebas varias | 100% | 2022-12-05 | 2022-12-05 | 1
Ejecución-Documentación |  | 2022-10-17 | 2022-12-05 | 50
Redacción de la memoria | 100% | 2022-10-17 | 2022-12-05 | 50
Formato de la memoria | 100% | 2022-10-17 | 2022-10-18 | 2
Introducción del proyecto | 100% | 2022-10-18 | 2022-10-19 | 2
Metodología | 100% | 2022-10-20 | 2022-10-21 | 2
Tecnología y herramientas | 100% | 2022-10-22 | 2022-10-23 | 2
Estimación de recursos y planificación | 100% | 2022-10-23 | 2022-10-25 | 3
Análisis del proyecto | 100% | 2022-10-26 | 2022-10-31 | 6
Diseño del proyecto | 100% | 2022-11-01 | 2022-11-30 | 30
Despliegue y pruebas | 100% | 2022-11-30 | 2022-12-02 | 3
Conclusiones | 100% | 2022-12-03 | 2022-12-03 | 1
Vías futuras | 100% | 2022-12-04 | 2022-12-05 | 2
SIMPLE GANTT CHART by Vertex42.com |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on F6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Diagrama real
VEHICLEGEST
ILERNA ONLINE | Comienzo del proyecto: | 2022-10-20
Carlos Caruncho | Hoy: | 2022-12-05
| Visualizar semana | 1 |  |  | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05
 | time axis 2022-10-17 to 2022-12-11
TAREA | PROGRESO | COMIENZO | FIN | DÍAS | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d
Iniciación |  | 2022-10-17 | 2022-10-18 | 2
Elección de la temática | 100% | 2022-10-17 | 2022-10-18 | 2
Estudio de mercado | 100% | 2022-10-17 | 2022-10-18 | 2
Elección de tecnologías | 100% | 2022-10-17 | 2022-10-18 | 2
Definición ciclo de vida del proyecto | 100% | 2022-10-17 | 2022-10-18 | 2
Creación del repositorio | 100% | 2022-10-17 | 2022-10-18 | 2
Planificación |  | 2022-10-19 | 2022-10-25 | 7
Creación del repositorio | 100% | 2022-10-19 | 2022-10-20 | 2
Selección de la metodología | 100% | 2022-10-20 | 2022-10-21 | 2
Diagrama de Gantt | 100% | 2022-10-22 | 2022-10-24 | 3
Tablero Kanban | 100% | 2022-10-24 | 2022-10-25 | 2
Ejecución-Análisis |  | 2022-10-26 | 2022-10-31 | 6
Definición de requisitos | 100% | 2022-10-26 | 2022-10-27 | 2
Diagrama Entidad-Relación | 100% | 2022-10-27 | 2022-10-28 | 2
Diagrama Relacional | 100% | 2022-10-28 | 2022-10-29 | 2
Diagrama de clases | 100% | 2022-10-29 | 2022-10-30 | 2
Diagrama de casos de uso | 100% | 2022-10-30 | 2022-10-31 | 2
Ejecución-Diseño |  | 2022-11-01 | 2022-11-01 | 1
Boceto | 100% | 2022-11-01 | 2022-11-01 | 1
Ejecución-Codificación |  | 2022-11-02 | 2022-12-05 | 34
Autenticación | 100% | 2022-11-02 | 2022-11-04 | 3
Implementar menús | 100% | 2022-11-05 | 2022-11-07 | 3
Listado de vehículos | 100% | 2022-11-08 | 2022-11-09 | 2
Detalle de vehículo | 100% | 2022-11-10 | 2022-11-11 | 2
Creación de vehículo | 100% | 2022-11-11 | 2022-11-12 | 2
Edición de vehículos | 100% | 2022-11-15 | 2022-11-16 | 2
Eliminación de vehículo | 100% | 2022-11-17 | 2022-11-17 | 1
Listado de items de inventario | 100% | 2022-11-18 | 2022-11-18 | 1
Detalle de items de inventario | 100% | 2022-11-19 | 2022-11-20 | 2
Creación de items de inventario | 100% | 2022-11-21 | 2022-11-22 | 2
Edición de item de inventario | 100% | 2022-11-22 | 2022-11-23 | 2
Eliminación de item de inventario | 100% | 2022-11-23 | 2022-11-24 | 2
Listado de deficiencias | 100% | 2022-11-25 | 2022-11-25 | 1
Creación de deficiencias | 100% | 2022-11-26 | 2022-11-27 | 2
Detalle de deficiencias | 100% | 2022-11-27 | 2022-11-28 | 2
Edición de deficiencias | 100% | 2022-11-28 | 2022-11-28 | 1
Eliminación de deficiencias | 100% | 2022-11-28 | 2022-11-28 | 1
Listado de usuarios | 100% | 2022-11-29 | 2022-11-30 | 2
Detalle de usuarios | 100% | 2022-11-30 | 2022-12-01 | 2
Creación de usuarios | 100% | 2022-12-01 | 2022-12-02 | 2
Edición de usuarios | 100% | 2022-12-01 | 2022-12-02 | 2
Eliminación de usuarios | 100% | 2022-12-01 | 2022-12-02 | 2
Listado de ITVs | 100% | 2022-12-01 | 2022-12-02 | 2
Listado de alertas | 100% | 2022-12-01 | 2022-12-02 | 2
Generación de alertas | 100% | 2022-12-01 | 2022-12-02 | 2
Eliminación de alertas | 100% | 2022-12-01 | 2022-12-02 | 2
Ejecución-Pruebas |  | 2022-12-04 | 2022-12-05 | 2
Prueba de autenticación | 100% | 2022-12-04 | 2022-12-05 | 2
Pruebas de creación | 100% | 2022-12-04 | 2022-12-05 | 2
Pruebas de edición | 100% | 2022-12-04 | 2022-12-05 | 2
Pruebas de eliminación | 100% | 2022-12-04 | 2022-12-05 | 2
Pruebas varias | 100% | 2022-12-04 | 2022-12-05 | 2
Ejecución-Documentación |  | 2022-10-17 | 2022-12-05 | 50
Redacción de la memoria | 100% | 2022-10-17 | 2022-12-05 | 50
Formato de la memoria | 100% | 2022-10-17 | 2022-10-18 | 2
Introducción del proyecto | 100% | 2022-10-18 | 2022-10-19 | 2
Metodología | 100% | 2022-10-20 | 2022-10-21 | 2
Tecnología y herramientas | 100% | 2022-10-22 | 2022-10-23 | 2
Estimación de recursos y planificación | 100% | 2022-10-23 | 2022-10-25 | 3
Análisis del proyecto | 100% | 2022-10-26 | 2022-10-31 | 6
Diseño del proyecto | 100% | 2022-11-01 | 2022-11-30 | 30
Despliegue y pruebas | 100% | 2022-11-30 | 2022-12-02 | 3
Conclusiones | 100% | 2022-12-03 | 2022-12-03 | 1
Vías futuras | 100% | 2022-12-04 | 2022-12-05 | 2
SIMPLE GANTT CHART by Vertex42.com |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on F6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.